## Sheet1
Product Backlog
KEY
Task No. | Title | Notes | Sprint Allocation | Primary Task Holder | Status | NOT STARTED |  | Product has yet to be allowcated is awaiting sprint
PREREQUISITE | Confirmation with Tom | Contact Tom with project group details, and await confirmation | PREREQUISITE | - | IN PROGRESS | IN PROGRESS |  | Task Started, in current sprint
PREREQUISITE | Position Allocation | Allocate all Prosistion to the different members of the team | PREREQUISITE | - | DONE | DONE |  | Task Completed
1 | Game Treatment | Style, Samples, Theme Porential Level Designs, Storybroad, Plot, Player Creation | S1 | Andy | IN PROGRESS
2 | GIT 1 | Have GIT Running on every members machine | S1 | Hiren | IN PROGRESS
3 | GIT 2 | Teach all members how to use GIT | S1 | Hiren | IN PROGRESS | Sprint Timetable
4 | Standards 1 | Produce File Standards Document | S1 | Sunny | IN PROGRESS | Sprint Name | Start Date | End Date | Jobs | Notes
5 | Standards 2 | Produce Coding Standards Documents | S1 | Paul | IN PROGRESS | S1 | 2011-09-26 | 2011-10-03
6 | Standards 3 | Produce Media(Image/Sound) Standards Document | S1 | Hiren | IN PROGRESS | S2 | 2011-10-03 | 2011-10-10
7 | Standards 4 | Produce Design Standards Document | S1 | Andy | IN PROGRESS | S3 | 2011-10-10 | 2011-10-17
[6 empty] | S4 | 2011-10-17 | 2011-10-24
[6 empty] | S5 | 2011-10-24 | 2011-10-31
[6 empty] | S6 | 2011-10-31 | 2011-11-07
[6 empty] | S7 | 2011-11-07 | 2011-11-14
[6 empty] | S8 | 2011-11-14 | 2011-11-21
[6 empty] | S9 | 2011-11-21 | 2011-11-28
[6 empty] | S10 | 2011-11-28 | 2011-12-05
[6 empty] | S11 | 2011-12-05 | 2011-12-12 |  | DEMO
[6 empty] | S12 | 2011-12-12 | 2011-12-19 |  | SUBMISSION