## Sheet1
Product Backlog
KEY
Task No. | Title | Notes | Sprint Allocation | Primary Task Holder | Status | NOT STARTED |  | Product has yet to be allowcated is awaiting sprint
PREREQUISITE | Confirmation with Tom | Contact Tom with project group details, and await confirmation | PREREQUISITE | - | DONE | IN PROGRESS |  | Task Started, in current sprint
PREREQUISITE | Position Allocation | Allocate all Prosistion to the different members of the team | PREREQUISITE | - | DONE | DONE |  | Task Completed
1 | Game Treatment | Style, Samples, Theme Porential Level Designs, Storybroad, Plot, Player Creation | S1 | Andy | DONE
2 | GIT 1 | Have GIT Running on every members machine | S1 | Hiren | DONE
3 | GIT 2 | Teach all members how to use GIT | S1 | Hiren | IN PROGRESS | Sprint Timetable
4 | Standards 1 | Produce File Standards Document | S1 | Sunny | IN PROGRESS | Sprint Name | Start Date | End Date | Jobs | Notes
5 | Standards 2 | Produce Coding Standards Documents | S1 | Paul | IN PROGRESS | S1 | 2011-09-26 | 2011-10-03 | 1,2,3,4,5,6,,7 | 50% done
6 | Standards 3 | Produce Media(Image/Sound) Standards Document | S1 | Hiren | IN PROGRESS | S2 | 2011-10-03 | 2011-10-10 | 20,21,22,26,27,30,31,24 | In progress
7 | Standards 4 | Produce Design Standards Document | S1 | Andy | DONE | S3 | 2011-10-10 | 2011-10-17
8 | Music 1 | Music Design | - | Andy | NOT STARTED | S4 | 2011-10-17 | 2011-10-24
9 | Music 2 | Splash Screen Music | - | Andy | NOT STARTED | S5 | 2011-10-24 | 2011-10-31
10 | Music 3 | Title Music | - | Andy | NOT STARTED | S6 | 2011-10-31 | 2011-11-07
11 | Music 4 | Research FMOD | - | Andy | NOT STARTED | S7 | 2011-11-07 | 2011-11-14
12 | Music 5 | Gather SFX examples | - | Andy | NOT STARTED | S8 | 2011-11-14 | 2011-11-21
13 | Music 6 | Intergate Sound Manager | - | Andy | NOT STARTED | S9 | 2011-11-21 | 2011-11-28
14 | Art 1 | Art Plan | - | Hiren | NOT STARTED | S10 | 2011-11-28 | 2011-12-05
15 | Art 2 | Produce Placeholders | S2 | Hiren | IN PROGRESS | S11 | 2011-12-05 | 2011-12-12 |  | DEMO
16 | Art 3 | Player Art | S2 | Hiren | IN PROGRESS | S12 | 2011-12-12 | 2011-12-19 |  | SUBMISSION
17 | Art 4 | Enemy Art | S2 | Hiren | IN PROGRESS
18 | Art 5 | Level Design | - | Hiren | NOT STARTED
19 | Art 6 | Textures and Materials | - | Hiren | NOT STARTED
20 | Art 7 | 3D Modelling | - | Hiren | NOT STARTED
21 | Documentation 1 | Gantt Charts | S2 | Sunny | IN PROGRESS
22 | Documentation 2 | Git Standards | S2 | Sunny | IN PROGRESS
23 | Documentation 3 | Test Plan | - | Sunny | NOT STARTED
24 | Programming 1 | Strip out Demo Application | S1 | Paul | DONE
25 | Programming 2 | Building Skybox, landscape and camera | S2 | Paul | IN PROGRESS
26 | Programming 3 | Character Movement | S2 | Paul | IN PROGRESS
27 | Programming 4 | Physics Engine | - | Paul | NOT STARTED
28 | Programming 5 | Sound Manager | - | Paul | NOT STARTED
29 | Programming 6 | Level Manager | S2 | Paul | IN PROGRESS
30 | Game Treatment 2 | Comic Book Style Storyboard | - | Andy | NOT STARTED
31 | Art 8 | Provice Concept Art Backlog | - | Hiren | NOT STARTED